## PRODUCT BACKLOG
PRODUCT BACKLOG
ID | Feature | Category | Priority | Sprint 1 | Sprint 2 | Sprint 3
0 | display menu screen on program start | workable menu | Must
1 | menu with "start game" and "exit" buttons | workable menu | Must
2 | show the rules of the game when needed by the user | instructions/rules | Must
3 | show instructions that help the player during his turn | instruction/ rules and playability for human users | Must
4 | when players press exit the game will show a termination screen | termination screen | Must
5 | display game board | 2D graphics | Must
6 | display ships on the side | 2D graphics | Must
7 | display exit button during an active game | termination screen | Must
8 | display whose turn is active | playability | Must
9 | players can place ships on game board | playability | Must
10 | players receive 2 random cards at start | playability | Must
11 | players can choose a position and stats will change accordingly | playability | Must
12 | player gets a normal card every turn | playability | Must
13 | player can attack ships and move ships | playabilty | must
14 | all cards are added and randomized | playabilty | must
15 | when cards are used, automatically change stats of a player | playability | must
16 | ships range are showed when player selects ship | playability | must
17 | show win screen when player exterminates other player his ships | playability | must
18 | 3 options in win screen, go to 'High score', 'Menu' or 'Play again" | workable menu | must
19 | current player can pause and resume game | workable menu/ playability | should
20 | high score menu which automatically adjusts | high score | must
21 | add sounds for every interaction in game | sounds | should
22 | add animations for movement/interactions | animation | should
23 | add option to play against computer | AI | would
24 | computer is able to play game | AI | would
25 | save current state of game | savegame | should
26 | load previous saved game | savegame | should
27 | add settings to main menu | setting | could
28 | make game playable online | networking | would
29 | make game playable by LAN | networking | would

## SPRINT 1 BACKLOG
SPRINT 1 BACKLOG
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
0 | As a user I want a display menu when I start the program, so that I can see all the game options. | Must | 8 | 1. Create a display menu with the theme of the game. 2. Create a visible start button 3. Create a visible exit button 4. Use the right texture for the buttons | 1. The start button is visible on the display menu 2. The quit button is visible on the display menu 3. The theme of the game must be visible
1 | As a user I want a menu with "start game" and "exit" buttons, so that I can start the game or terminate the game. | Must | 13 | 1. Write a function for the start button to make it jump to another screen 2. Write a function for the exit button to make it terminate the program | 1. The quit button should terminate the program 2. The start button startup another In-game Activity 3. All buttons work without error
5 | As a user i want a game board to play on, so that i know where i can place and move my ships. | Must | 20 | 1. Create a grid | 1. The grid must be 20 by 20 blocks
EXAMPLE
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
1 | As a player I want to start the game from the menu, so that I can play it. | M | [1] | - Find a proper button texture - Load and display button texture on run - When clicked on screen, retrieve position - If clicked on start button, init game | - Button displayed on menu screen - Button has a reasonable size compared to screen dimension - Clicks not on the button area have no effect on game start - Clicks on the button area make the screen change (to init phase)
1 | As a player I want to quit the program from the menu, so that I can stop playing. | M | [1] | - Find a proper button texture - Load and display button texture on run - When clicked on screen, retrieve position - If clicked on exit button, quit program | - Button displayed on menu screen - Button has a reasonable size compared to screen dimension - Clicks not on the button area have no effect on quit program - Clicks on the button area make the program quit

## SRINT 2 BACKLOG
SPRINT 2 BACKLOG
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
2 | As a user I want to acces the rules of the game, so I can see how to game works. | Must | 13 | 1. Write a code that shows all the rules of the game 2. Make a button that can show all the game rules | 1. All buttons work without error 2. All the rules of the game are shown 3. The player can close the rules screen 4. The spelling of the rules is correct
3 | As a user I want to see the intructions during my turn so I know what to do. | Must | 20 | 1. Write a code that shows a hint or instruction at every turn during every step. 2. Write a code that checks what player must play the turn. | 1. Instructions are shown at the start of the game 2. Instruction screen closes when a turn had ended 3. The spelling of the instructions is correct
4 | As a user I want the game to show a termination screen to check if im sure I want to quit, so that i dont accidently close the game | Must | 13 | 1. Write a code that shows a termination screen. 2. Make it so that the termination screen closes the game and resume the current screen. | 1. termination screen is shown when quit button is pressed. 2. The spelling is correct 3. There are 2 buttons . 4. Buttons work without errors.
6 | As a user I want to see ships on the side of my game-board so that I know which ships I have. | Must | 13 | 1.Design proper ships texture. 2.Write a code that display the ships on the side of the game-board. | 1. Each ship must have a different look. 2. The ships must be displayed on the side.
7 | As a user I want to have an ''exit" button so that I can go back to main menu when it's pressed | Must | 5 | 1. Write a code that terminated the game-play and bring the player back to main menu 2. Display the button in game-play | 1. All buttons work without error 2. The exit-button is visible in game-play screen
8 | As a user i want to know who plays the current turn, so I know who hast to act | Must | 5 | 1. Write a code that shows the current turn in the game-play screen. | 1. The game-play screen shows which player has current turn
9 | As a user I want to place my ships on the tile I want, so that I can make my own strategy | Must | 20 | 1. Make a function which lets the player place their boats on the grid. | 1. The player can only place a ship when their opponent placed one. 2. Players cant place boats on the same position. 3. The back of the boat must face the harbor. 4. The players can place the ships without error.
10 | As a user I want to receive cards, so that I can use it in the game. | Must | 13 | 1. Make a function that gives a player cards. | 1. The cards can only be received at the start of a game. 2. The cards must be random generated. 3. Players can only receive 2 cards.
11 | As a user I want to alter the position of my boats, so that I can change my strategy. | Must | 13 | 1. Make a function which lets the player change the position of their boats. 2. Make it so that the attack range and stats change when the position changes | 1. After players change the position they cant move. 2. You can only switch to attack and defense position 3. Players can switch positions without errors.
12 | As a user I want to receive cards, so that I can use it in the game. | Must | 8 | 1.Write a function that gives a player a normal card. | 1. The card must be a normal card. 2. The card must be given at the start of every turn. 3. The amount of cards given must be 1 4. A player can only have 6 cards
13 | As a user I want to move my ships and attack, so that I can increase the chance of winning. | Must | 20 | 1. Make the ships able to attack. 2. Give the ships hitpoints. 3. Write a function which lets the player move their ships | 1. Ships can only attack once. 2. Ships must be destroyed if it reaches 0 hitpoints. 3. Each ship must have the correct attack range. 4. Each ship must have the correct move range.
14 | As a user I want to have cards in the game, so that i can use them to increase my chance of winning | Must | 20 | 1. Make Offensive cards. 2. Make Defensive cards 3. Make Help cards 4. Make Special cards | 1. All cards must have correct spelling 2. There can only be a certain amount of cards.
15 | As a user I want to use cards, so that i can change the stats of all the boats in the game | Must | 13 | 1. Make the cards usable | 1. All cards must influence the game without failure. 2. A player can only use 2 cards per turn.
16 | As a user I want to know the range of my attacks and movement of my ship, so that I can make logic decision | Must | 8 | 1.Make a code which lets the player show how many tiles it can move and attack. | 1. The range must be correct. 2. The range which is shown must be clear and simple to understand.
17 | As a user I want to see a win screen, so I know who the victor is. | Must | 8 | 1.Write a code which shows the victory screen when all enemy ships are defeated. | 1. There can only be a victory screen when a players ships are defeated. 2. There can only be one victor